***Appendix F: Capstone Project Gantt Chart Template***

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E:\Downloads\University-of-Cebu-Logo.png  University of Cebu  College of Computer Studies  Cebu City | | | | | | | | | | | | | | | | |
| Task ID | Task Name | Task Lead | Start Date | End Date | August 2015 | | | | September 2015 | | | | October 2015 | | | |
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
|  | Title Consultation |  | Aug 16 | Sep 16 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Project Proposal recommended |  | Sep 16 | Sep 16 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Discussion with adviser | Jephunneh | Sep 19 | Sep 23 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preliminary research of the project | Cristian | Sep 23 | Sep 26 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Writing of Chapter 1 | Cristian | Sep 23 | Sep 26 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Consultation with adviser on Chapter 1 | Jephunneh | Sep 27 | Sep 27 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparing of Transmittal Letter/s | Rhea Shane | Sep 16 | Sep 23 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparing of Questionnaires | Rhea Shane | Sep 16 | Sep 23 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Interviews/Surveys | Rhea Shane | Sep 23 | Oct |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finalizing of Chapter 1 | Cristian | Sep 27 | Sep 28 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Writing of Chapter 2 | Cristian | Sep 29 | Oct 2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Consultation with adviser on Chapters 1 and 2 | Jephunneh | Oct 2 | Oct 2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finalizing of Chapter 2 |  | Oct 2 | Oct 4 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Writing of Chapter 3 | Rhea Shane | Oct 7 | Oct 17 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Consultation with adviser on Chapters 1, 2, and 3 | Jephunneh | Oct 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Consultation with Technical Editor | Rhea Shane | Oct 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Writing of Initial and Final Pages | Jephunneh | Oct 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final consultation with adviser | Jephunneh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Compiling and finalizing of Manuscript | Rhea Shane |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Poster design & preparation | Cristian | Oct 17 | Oct 20 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Presentation preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Proposal presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |